## village intensive electr
HUBLI ELECTRICITY SUPPLY COMPANY LIMITED
Year wise progress of village intensive electrification under RGGVY Scheme
Sl.no | District | 2007-08 |  | 2008-09 |  | 2009-10 |  | 2010-11 |  | 2011-12 |  | 2012-13 |  | 2013-14 |  | 2014-15 |  | 2015-16 |  | 2016-17 |  | 2017-18
|  | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement
1 | Dharwad | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Bagalkot | 54 | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Haveri | 35 | 17 | 18 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Gadag | 200 | 185 | 15 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | Bijapur | 291 | 184 | 107 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
X Plan Total |  | 592 | 452 | 140 | 47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | UttarKannada | 1248 | 144 | 1104 | 333 | 742 | 142 | 600 | 109 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | Belgaum | 1136 | 147 | 989 | 309 | 675 | 427 | 248 | 78 | 170 | 86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
XI Plan Total |  | 2384 | 291 | 2093 | 642 | 1417 | 569 | 848 | 187 | 170 | 86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | Haveri | [16 empty] | 0 | 0 | 692 | 3 | 692 | 573
XII Plan | [17 empty] | 0 | 0 | 692 | 3 | 692 | 573
Grant Total |  | 2976 | 743 | 2233 | 689 | 1417 | 569 | 848 | 187 | 170 | 86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 692 | 3 | 692 | 573
[21 empty] | 2303 |  | 2303
[21 empty] | 1953 |  | 1953

## habitation electrification
HUBLI ELECTRICITY SUPPLY COMPANY LIMITED
Year wise progress of Habitation electrification under RGGVY Scheme
Sl.no | District | 2007-08 |  | 2008-09 |  | 2009-10 |  | 2010-11 |  | 2011-12 |  | 2012-13 |  | 2013-14 |  | 2014-15 |  | 2015-16 |  | 2016-17 |  | 2017-18 |  | REMARKS
|  | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement
1 | Dharwad | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10th Plan Scheme completed in FY 2008-09
2 | Bagalkot | 118 | 0 | 118 | 97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Haveri | 47 | 11 | 36 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Gadag | 42 | 34 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | Bijapur | 127 | 104 | 118 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
X Plan Total |  | 344 | 149 | 280 | 156 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | UttarKannada | 604 | 94 | 510 | 348 | 164 | 150 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11th Plan Scheme completed in FY 2011-12
7 | Belgaum | 554 | 107 | 447 | 319 | 125 | 39 | 86 | 5 | 81 | 15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
XI Plan Total |  | 1158 | 201 | 957 | 667 | 289 | 189 | 98 | 17 | 81 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | Haveri | [16 empty] | 0 | 0 | 702 | 2 | 702 | 584 | 12th Plan Scheme completed in FY 2017-18
XII Plan | [17 empty] | 0 | 0 | 702 | 2 | 702 | 584
Grant Total |  | 1502 | 350 | 1237 | 823 | 289 | 189 | 98 | 17 | 81 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 702 | 2 | 702 | 584
[21 empty] | 2303 |  | 2303
[21 empty] | 1953 |  | 1953

## BPL progress
HUBLI ELECTRICITY SUPPLY COMPANY LIMITED
Year wise progress of BPL electrification under RGGVY Scheme
Sl.no | District | 2006-07 |  | 2007-08 |  | 2008-09 |  | 2009-10 |  | 2010-11 |  | 2011-12 |  | 2012-13 |  | 2013-14 |  | 2014-15 |  | 2015-16 |  | 2016-17 |  | 2017-18 |  | REMARKS
|  | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement
1 | Dharwad | 21936 | 12929 | 9007 | 9007 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10th Plan Scheme completed in FY 2008-09
2 | Bagalkot | 39429 | 29012 | 10417 | 8809 | 1608 | 2118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Haveri | 27911 | 7915 | 19996 | 11685 | 8311 | 1751 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Gadag | 33477 | 28120 | 5357 | 8307 | -2950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | Bijapur | 48899 | 15638 | 33261 | 10101 | 23160 | 6700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
X Plan Total |  | 171652 | 93614 | 78038 | 47909 | 30129 | 10569 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | UttarKannada | 0 | 0 | 0 | 0 | 19657 | 8879 | 10778 | 9073 | 1705 | 462 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11th Plan Scheme completed in FY 2011-12
7 | Belgaum | 0 | 0 | 0 | 0 | 62430 | 20199 | 42231 | 16799 | 25432 | 7079 | 18353 | 5341 | 13012 | 4690 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
XI Plan Total |  | 0 | 0 | 0 | 0 | 82087 | 29078 | 53009 | 25872 | 27137 | 7541 | 18353 | 5341 | 13012 | 4690 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | Haveri | [18 empty] | 500 | 350 | 10000 | 1953 | 8138 | 15918 | 12th Plan Scheme completed in FY 2017-18
XII Plan | [19 empty] | 500 | 350 | 10000 | 1953 | 8138 | 15918
Grant Total |  | 171652 | 93614 | 78038 | 47909 | 112216 | 39647 | 53009 | 25872 | 27137 | 7541 | 18353 | 5341 | 13012 | 4690 | 0 | 0 | 0 | 0 | 500 | 350 | 10000 | 1953 | 8138 | 15918
[23 empty] | 2303 |  | 18221
[23 empty] | 1953 |  | 18638

## RHH progress (2)
year wise RHH electrification
Sl.no | District | 2006-07 |  | 2007-08 |  | 2008-09 |  | 2009-10 |  | 2010-11 |  | 2011-12 |  | 2012-13 |  | 2013-14 |  | 2014-15 |  | 2015-16 |  | 2016-17 |  | 2017-18 |  | REMARKS
|  | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement
1 | Dharwad | 31806 | 13305 | 18501 | 9833 | 8668 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10th Plan Scheme completed in FY 2008-09
2 | Bagalkot | 61557 | 29407 | 32150 | 9449 | 22701 | 2822 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Haveri | 116443 | 11155 | 105288 | 11709 | 93579 | 1751 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Gadag | 63203 | 29786 | 33417 | 8365 | 25052 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | Bijapur | 90658 | 19174 | 71484 | 11672 | 59812 | 6700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
X Plan Total |  | 363667 | 102827 | 260840 | 51028 | 209812 | 11273 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | UttarKannada | 0 | 0 | 0 | 0 | 34614 | 8946 | 25668 | 9340 | 16328 | 1314 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11th Plan Scheme completed in FY 2011-12
7 | Belgaum | 0 | 0 | 0 | 0 | 163192 | 20391 | 142801 | 17341 | 125460 | 8617 | 116843 | 8100 | 108743 | 1700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
XI Plan Total |  | 0 | 0 | 0 | 0 | 197806 | 29337 | 168469 | 26681 | 141788 | 9931 | 116843 | 8100 | 108743 | 1700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | Haveri | [18 empty] | 600 | 450 | 12000 | 2015 | 11606 | 15756 | 12th Plan Scheme completed in FY 2017-18
XII Plan | [19 empty] | 600 | 450 | 12000 | 2015 | 11606 | 15756
Grant Total |  | 363667 | 102827 | 260840 | 51028 | 407618 | 40610 | 168469 | 26681 | 141788 | 9931 | 116843 | 8100 | 108743 | 1700 | 0 | 0 | 0 | 0 | 600 | 450 | 12000 | 2015 | 11606 | 15756
[24 empty] | 24206 | 18221

## GK-IP sets serviced
HUBLI ELECTRICITY SUPPLY COMPANY LIMITED
Gangakalyan Borewells serviced from FY 2012-13 to 2018-19 (As on Februarry-2019)
Sl.No | District | 2012-13 |  | 2013-14 |  | 2014-15 |  | 2015-16 |  | 2016-17 |  | 2017-18 |  | 2018-19 (As on Feb-19)
|  | Target | Progress | Target | Progress | Target | Progress | Target | Progress | Target | Progress | Target | Progress | Target | Progress
1 | Dharwad | - | 123 | - | 574 | - | 162 | - | 237 | - | 436 | - | 539 | - | 351
2 | Gadag | - | 172 | - | 437 | - | 223 | - | 154 | - | 739 | - | 939 | - | 342
3 | Uttarkannada | - | 266 | - | 131 | - | 102 | - | 174 | - | 233 | - | 307 | - | 236
4 | Haveri | - | 556 | - | 788 | - | 303 | - | 722 | - | 679 | - | 972 | - | 464
5 | Belgaum | - | 748 | - | 1540 | - | 723 | - | 1207 | - | 1220 | - | 1665 | - | 1512
6 | Bijapur | - | 545 | - | 1079 | - | 615 | - | 791 | - | 1477 | - | 683 | - | 1047
7 | Bagalkot | - | 499 | - | 767 | - | 381 | - | 470 | - | 656 | - | 1123 | - | 904
Total |  | 0 | 2909 | 0 | 5316 | 0 | 2509 | 0 | 3755 | 0 | 5440 | 0 | 6228 | 0 | 4856